Briefing Note

14 March  2023

To: All PC Members/Parish Clerk

Neighbourhood Plan (NP) - Badwell Ash & Long Thurlow Parish Council: Meeting 14 March 2023

1. At the Feb 23 Meeting the PC agreed to go ahead with the Badwell Ash & Long Thurlow NP and to engage a Planning Consultant at the start of the process. Secondly to set up a NP Steering Group to manage the process. Initial contact has been made with an experienced Planning Consultant and MSDC on the NP light approach and response emails summarise the position as:

a) Planning Consultant list has been provided on which there are experienced NP Consultants, some of which are not available to work with us until Sept 23 this year.

b) A first consultation has been arranged on the 21 March via Zoom to get BA & LT started on what useful steps and work we can undertake in the interim period to then move forward with a Planning Consultant.

c) The locality grant funding provided by the Govt runs until the end of this month and no firm announcement has YET been made on the next financial years funding. Mid Suffolk expect the Govt funding to continue for 23/24, which we can still apply for.

d)  The MSDC NP Light approach email reply, I have attached so you can see what options are open to us as a PC.

e)  NP Steering Group, I have 2 volunteers so far, one from BA and one from LT, with two other persons offering part time input. This will not be enough to form a productive Steering Group, I have asked for an update for volunteers to go out in the next Broadsheet.

2. The other start up considerations remain TBC and decided

- What budget needs to be allocated for the NP? – Printing/Surveys/Admin Support materials

- NP Working or Steering Group?

- Do we need an email account for the NP, otherwise official PC email would be log jammed if not?

- What would the membership be? Based on skills set or time they can give?

- Dates for NPSG Meetings – suggest before PC Monthly meetings.

- How to staff meetings for example pop up surgeries/ volunteers to help with mail drops/surveys

- Would a treasurer role be required for example if any money is donated for the NP in the process stages?

Steve Russell

Badwell Ash PC Deputy Chair

Notes Page