Badwell Ash & Long Thurlow Neighbourhood Plan(NP) Steering Group Meeting Minutes  Monday 2 Deember 2024 – Held at BA Small Village Hall 1100 – 1500 hours

| Attendees | Organisation |
| --- | --- |
| Andrea Long (AL) David Girling (DG) John Morgan(JM) Steve Russell (SR) Mark Tomkins (MT) | Compass Point Planning BA&LT Working Group BA & LT Parish Council BA & LT Parish Council BA & LT Parish Council |
| Agenda Item | Actions & Outcomes |
| 1. Brief Overview of Regulation 14 (R14) Consultation Responses 2024 – AL advised that the meeting was open to the Public should they wish to attend and gave an overview of the Consultation responses, Statutory Consultees, Public and MSDC Comments and feedback. 2. Moving from R14 Consultation to submission – Discussion on the process for the work required before the formal R14 submission to MSDC 3. Reviewing the Consultation Responses – Full Discussion and review of R14 Table Documents. 4.Timescale & Next Steps – AL outlined the timetable for submission under the R14 process and the Formal six- week consultation process undertaken by MSDC. The Steering Group need to have the final draft NP and supporting documents ready for PC approval by the end of January 2025. Feb 2025 PC Meeting date is 7th February. 5.Date of Next Meeting (DoNM) – Three dates for early January to be put out on NP What’s App Group date decided 6th Jan 2025 | AL advised the R14 Table document would be used for the discussion at Agenda Item 3 Action 1 in progress – Rachel Leggett (RL) to provide Consultation Statement and Andrea Long (AL) Basic Condition Statement for R14 submission. All SG members to provide MT with comments for one Group response to go to RL. All comments to be with MT before date of Next Meeting in Jan 25. Responses included, comments and recommendations which will be fully considered in the R14 response for MSDC See Action 1 Action 2 – DoNM -Monday 6th Jan 1000 hours Small Hall at Badwell Ash |